## Sheet1
Day | What was done | What was expected | What was measured | What was changed | Whats Next
2026-10-11 | Made the Logbook for the cooling system alongside the Brief overview of the project and ordered all the necessary parts for our tempreature readings | To finish the Excel File and Brief for the Day | N/A | N/A | Waiting on the necessary items needed to begin testing and coding the prototype
2026-10-12 | Learned the basics of Git and GitHub, including branches, commits and pushing changes. Studied the Arduino code for the DS18B20 sensor, including the OneWire and DallasTemperature libraries, setup(), loop(), variables, conditions and serial output. This entry was added retrospectively on October 19. | Understand how to save and track project code using GitHub and explain how the Arduino program requests, reads and displays temperature measurements. | N/A. This session focused on learning software tools and understanding the sensor code. No hardware measurements were taken. | Developed my understanding of version control and the sensor program. No hardware changes were made. | Wait for the components to arrive, assemble the sensor circuit and upload the program to check real temperature readings.
2026-10-19 | Connected the DS18B20 probe to its terminal adapter and Arduino UNO. Uploaded the temperature-reading program and viewed readings in Serial Monitor at 9600 baud. Checked readings with the probe untouched, held the probe to warm it, and observed cooling after release. Captured photographs and screenshots. Committed and pushed the sensor code to a GitHub branch. https://github.com/Kotakaari/Temperature-controlled-cooling-system-for-small-compute-enclosure.git | Obtain repeated temperature readings, observe an increase when holding the probe and a gradual decrease after releasing it. Check that the program can display an error when the sensor cannot be read. | An untouched-probe screenshot showed repeated readings of 20.06 °C. During hand warming, readings rose to 28.50 °C in the captured screenshots. A cooling screenshot showed readings falling from 28.25 °C to 28.00 °C. An error message appeared in another capture, followed by resumed temperature readings. These observations demonstrate basic operation and temperature response. Accuracy has not yet been checked against a reference thermometer. Evidence saved in docs/tests/2026-10-19-temperature-sensor/. Includes wiring photographs, Serial Monitor screenshots and a test summary. | Corrected the data connection from analog pin A2 to digital pin 2 to match the program. Identified the adapter's fitted 4.7 kΩ resistor, so no additional pull-up resistor was added. | Repeat and document a controlled sensor-disconnection test, including recovery after reconnection. Organize the wiring photographs and test screenshots in the repository and update the README. Then select a four-wire PWM fan, matching power supply and control-interface components for the fan-control stage.